## Instructions
This is the original template: https://docs.google.com/spreadsheets/d/1FuAKpV_AwW3bCyyWPcOSm_gblOWsR2QAQdDoW4Me_uU/edit#gid=0
This spreadsheet is used to do any test case scenarios to a product, a software application's functionality and features. This contains test steps, test data, precondition, post condition developed for specific test scenario in order to verify any requirement,
https://dobtesting.herokuapp.com/
From the Tester: https://docs.google.com/spreadsheets/d/1VH2XPCrQAFGBCa6vx3cXDq6ESJcJ3zn5vLHs3MtUgwA/edit#gid=1731396394

## Test CaseScenario
Test Case ID | Test Scenario | Test Steps | Test Data | Expected Result | Actual Results | Status | Rendered by | Milestone | Comments | Comments from the DEV
TC-001 | Add User | 1. Login to Admin account. 2. Click Users > Add Users 3. Fill in the form to add new user details. 4. Click submit | Mgr 1 Emp 1 | New User details added | New user details added succesfully but please comments for further improvement | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login | It was added succesfully but please add in to the Add user form the following additional data elements: * Timezone (drowpdown of list of Timezone) * Team (dropdown of list of Team created/added by the admin) * Status (dropdown list of Active, Disable)
TC-002 | View Users | 1. Login to Admin account 2. Click Users > View Users 3. Click View button of the selected User to review details | All users added | Able to view list of users from the Users Dashboard Update the user's details | Can able to view the entered user details but please see comments for further improvement. | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login | The user details container contains duplicate entry of username. Joining date and last login date timezone - what's the default timezone? The timezone has to be based on the current timezone of the user. | solved
TC-003 | Edit User | 1. Login to admin account 2. Click users > VIew Users 3. Click Edit button of the selected user to update the user's details 4. Fill up the necessary details to be changed 5. Click submit | All users added | It will update the changes entered into the Edit User form | It redirects to the Change User Password. See comments for further improvement After clicking Submit button, the message is "Success! Your Password Changed Successfully. | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login | Change the text title of User Roll to User Role Instead of textbox, change it to Dropdown list of Roles There’s no textbox to input the previous password and to confirm the new password. The form should contain all the elements that is present in the Add user form. including the newly suggested elements. The admin should be able to remove an access to a user by changing the status from Active to Disable. | solved
TC-004 | User Menu | Click User Menu to view the User Dashboard | User Menu Panel | View, edit, add, disable users | There are missing functionalities, see comments for further improvements | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login | Add into the User submenu * Add Role * Add Team | solved
TC-005 | Admin Access | Login to Admin account Test all the functionalities | Admin | View and access all the functionalities | There are missing functionalities, see comments for further improvements | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login | Add into the Menu panel: * Business Process - where an Employee and Manager is able to add new Business process category * Reporting - where the Manager can able to generate reports | right now there is one admin "Admin" of which credentials provided to you .It have all access but if you want admin can add new/other admin It can be done
TC-006 | Employee User Access | Login to user's account. Add new Task Add new Business Process | Emp 1 | Admin - has access to all functionalities Employee Access - Can add new task, view/edit all the added task, can add/edit business process. Employee can access only those tasks and businesses that under the team he/she belongs with | View the Tasks Dashboard - see comments for further improvements | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login | Employee access can't add new task, only to view the Tasks dashboard. Please add Business Process into the Menu Panel | Right now only task menu is just static displayed further functionalities will be added as tables will be added
TC-007 | Manager User Access | Login to user's account. Add new Tasks Add new Business Process View the user's list under his/her Team Generate report | Mgr 1 | Manager should be able to have access to the functionalities on Managerial level such as Tasks, Business Process, User's list of his team and Reporting | Access to Tasks Menu only, see comments for further improvement | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login | Manager should be able to have access to the functionalities on Managerial level such as Tasks, Business Process, User's list of his team and Reporting | will be added as new tables added
TC-008 | Contractor User Access | Login to user's account View Task and Update status | Contractor 1 | The assigned contractor should only see his/her assigned task, update the status of the task and download/upload the task spreadsheet that needed to be processed | Can only see the Tasks Dashboard. , see comments for furher improvement | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login | I have it passed since it's able to access only the Tasks dasboard however, the functionality and restricitons are not fully tested at this stage. | will be added as new tables added
TC-009 | QA contractor User Access | Login to user's account View the completed tasks from Contractor User | QA1 | The assigned contractor should only see his/her assigned task, update the status of the task and download/upload the task spreadsheet that needed to be processed | Can only see the Tasks Dashboard. , see comments for furher improvement | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login | I have it passed since it's able to access only the Tasks dasboard however, the functionality and restricitons are not fully tested at this stage. | will be added as new tables added
TC-010 | Tasks Dashboard | Click Tasks menu | All users added | Able to add and view all list of tasks, edit/update status depending on the user's access level | Can only view the task Dashboard but no functionalities , see comments for further improvement | Pass | mgr.ca.7523 | 2 -Dashboard Customization | Include in the sub menu to Add Task Columns of Tasks: Sr No. Title of Task Assignee Started On End Date Status View button Download Attachment button | will be added as new tables added
TC-011 | Admin User Login | Login to the admin user account | url - https://dobtesting.herokuapp.com username - admin password - admin | complexity of password even if it's in the testing stage |  | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login | Please change the password to JH6*&9p*O8yuUHLK&*i7tf | this is just testing server ,it will be changed when deployed on your server
TC-012 | Change User Password | Click Users > Change Password | All users added | It will update the password of the specific user | Updated the specific user | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login
TC-013 | Adding of New User | Click Users > Add Users | prj0722 | It should not add the same username and password even if they have different role | Same username, same email address successfully added. | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login | There should be a restriction to identify if a username is existing or an email address registered associated to a username or a user account, it shouldn't be registered even if it's on a different role.
TC-014 | Enabling Users | Click Users > Enable Users | All users that are disabled | The selected disabled account should be enabled once you click the submit button | successfully process the request | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login
TC-015 | Disabling Users | Click Users > Disable Users | All users that are enabled | The selected enabled account should be disabled once you click the submit button | successfully process the request | Pass | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login
TC-016 | Adding of Business Process Template | Click Business Process >Templates | csv file, excel file | Add csv, spreadsheet or a specific sheet of a spreadsheet | successfully process the request | Pass | mgr.ca.7523 | 3 -Employee & Processing Tables
TC-017 | Segration of Role per Team | Users > View users | all users | Each user role except the admin must be assigned to each of their designed team or department | No team/departement | Fail | mgr.ca.7523 | 1 -User Role Tables Including Permissions and Login |  | nothing mentioned about this in SOW
TC-018 | Obfuscating the Added Business Process spreadsheet | User>BusinssProcess>Add New Business Process | Admin Manager Employee | The uploaded spreadsheet where the user must be able to choose which fields are to be included and identify from those chosen fields that need to be obfuscated/masked. | It only detect all the columns from the spredsheet and maps it into the textbox | Pass | mgr.ca.7523 | 4 -Fetching Data from Spreadsheet and inserting into Tables
TC-019 | Task Management | User>Task | all Users | The contractor must be able to access the assigned task by the manager or employer and download the spreadsheet/csv file with the obfuscated data | No task access for all users. | Pass | mgr.ca.7523 | 5 -Task Management
TC-020 | Data Mapping of uploaded csv file | User>BusinessProcess>Add New Business Process | Admin Employee Manager | The uploaded spreadsheet or csv file can be manually mapped to the fields created by the user | It automatically fill in the textboxes but no way for the user to modify and select which one to be imported and obfuscated | Pass | mgr.ca.7523 | 4 -Fetching Data from Spreadsheet and inserting into Tables
TC-021 | Database of Fake Names of People and Businesses | The database of Processings names of People and Businesses will be used to masked selected columns which to be processed during the data obfuscation | Business Process spreadsheet | Selected columns of the business process will be masked with the processing names of person or business | Data selected was replaced with a random processing name from the database | Pass | mgr.ca.7523 | 3 -Employee & Processing Tables
TC-022 | Format of spreadsheets uploaded can be an excel or csv file | Upload spreadsheet type either csv or excel file where the system can automatically detect the columns available into the spreadsheet. |  |  |  | Pass | mgr.ca.7523 | 4 -Fetching Data from Spreadsheet and inserting into Tables
TC-023 | Detection of the spreadsheet tabs available in one spreadsheet file | 1. Upload the spreadsheet (in excel or csv) 2. The system detects whether the file has multiple tabs 3. The system will ask the employee/manager which particular tab is to be uploaded and processed into the system 4. The selected sheet tab will be processed for data obfucstion. | Add new Business Process | This is during the adding and assigning of new business process to be obfuscated and to be assigned to A & B contractors | Only the 1st tab is being selected | Fail | mgr.ca.7523 | 4 -Fetching Data from Spreadsheet and inserting into Tables | MGR 7523> Thu, Sep 09, 21 07:59> This is part of the Statemetn of work phase 1 | Already Discussed about this sep 20> its working just mention the sheet name in workbook
TC-024 | Creation of A & B spreadsheet file | 1. After uploading the original spreadsheet and been obfucscated, the system will create from the obfuscated copy an A & B spreadsheet which to be assigned to 2 contractors. 2. The 2 copies of spreadsheet must have the filename of the original spreadsheet and then add an A or B after. |  |  | Make two copies of the spreadsheets and csv files. There might be just one spreadsheets or csv file for this Business Process or there might be more than one. Name the files according to the naming convention which is the name of the uploaded file followed by an underscore followed by the name or the Business Process given when it was first created underscore date and time of the upload in YYYYMMDD format followed by an underscore and either A or B to indicate which Processing Contractor is assigned to do the work (A or B). e.g. if uploaded 22 march 2021 1:02PM in the users time zone: Payroll Leave_Leave Credit Processing_Auckland Office_20210322_1302_A Payroll Leave_Leave Credit Processing_Auckland Office_20210322_1302_B App sends The two assigned Processing Contractors an email advising a new task has | Pass | mgr.ca.7523 | 5 -Task Management |  | sheet A and B is creating
TC-025 | Check whether the new Business Process template is existing | 1. Employee will search if a Business Process template is already existing 2. If it's existing, the user will asked to provide a different unique Processing Name. 3. | 1. Add new Business Process Template 2. Indicate the same Process name that is existing. 3. The system must be able to detect if the same name has been used. |  |  | Pass | mgr.ca.7523 | 6 -Logic Management for Replace of Confidential Data
TC-026 | Recurrence of the Business Process Template | 1. Add a new business process template 2. Select the category of the Business Process to be created (g., HR, Payroll, Billing, Leave Credit Processing or Personnel Notices Processing) 3. Tag status either Recurring or One-time by ticking a radio button option 4. If it's Recurring, a dropdown option to select whether it's dail, weekly, semimonthly, monthly, quarterly, annually or others (if others, a textbox will be selected to manually time the recurrence) 5. Indicate the Due date. |  |  |  | Pass | mgr.ca.7523 | 6 -Logic Management for Replace of Confidential Data
TC-027 | The app then checks that the uploaded files are in either xls or xlsx or csv format and contain two dimensional tabular data. |  |  |  |  | Pass | mgr.ca.7523 | 6 -Logic Management for Replace of Confidential Data |  | data is obsfucating perfectly
TC-028 | All uploaded columns from a spreadsheet are tagged as Not included by default during data mapping process |  |  |  |  | Pass | mgr.ca.7523 | 6 -Logic Management for Replace of Confidential Data
TC-029 | Example: customer billing - columns with numbers need to be given for processing but identifiable information does not need to be given because no processing is required. The first row is the headers from the imported spreadsheet sheet. The user indicates which column is the unique identifying number and renames it UniqueID. In the example table below, the selected column was originally called Customer No. and now it is changed to UniqueID The second row, the user indicates whether or not to include the column in the spreadsheet sheet given to the Processing Contractors. The third row, the user indicates whether or not to mask included columns in the spreadsheet sheet given to the Processing Contractors. In the fourth row, the user indicates which type of data set is to be used for the masking. | 1. Identify which among the columns are to be included, masked/obfuscated, not included and included but not obfuscated. 2. Use the checkbox for each column to indicate the statuses. 3. If the column is ticked as Included, a checkbox obtion whether to mask or not the data included. 4. If the selected data is to be masked/obfuscated, the dropdown opiton to be enabled in the next row which data to be used to replace the selected column. 5. After the selection, color coding is applied to each row and column to easily identify the changes. |  |  |  | Pass | mgr.ca.7523 | 6 -Logic Management for Replace of Confidential Data
TC-030 | Color Coding during data mapping | Included + Mask is displayed in green background color, Not Included in light green colour, Included + not Masked in red background color |  |  |  | Not started | mgr.ca.7523 | 6 -Logic Management for Replace of Confidential Data | MGR 7523> Thu, Sep 09, 21 08:00> What will be an alternative for this? At least highlight the obfuscated data? | excel software and html(coding) is different ,the data is intepreted dynamically .so this isn't possible
TC-031 | QAing by the QA contractor | 1. A and B contractors submitted their completed spreadsheet. 2. QA contractor will be notified of the new task to QA the submitted A & B spreadsheet. 3. Review and give score to each contractor 4. Log the committed error by row and column, the number of errors committed. 5. Give back to the contractor who committed mistakes to correct and resubmit the QAed spreadsheet | Submitted spreadsheet from Contractor A and B | The A &B spreadsheets will only be available to QA contractor once both A & B contractors submitted and completed their task. Both A & B are to be submitted and QAed at the same time | The QA automatically receives and view the submitted by the contractor either A or B. | Fail | mgr.ca.7523 | 5 -Task Management | MGR 7523> Mon, Sep 13, 21 14:51> This is not yet corrected. After 1 contractor submitted a task for approval, this task is already avaialble to the QA dashboard which should not be showing. The task should ONLY be available once A & B submitted both task. Please do a self test once to verify (I've done it many times) MGR 7523> Fri, Aug 27, 21 15:14> If one contractor submitted the accomplished task, from QA dashboard it's being recorded. This is confusing cause it shouldn't appear any available task to be QAed unless both A & B contractors submitted their tasks. | this is completed
TC-032 | Sending of Email Notification to each Assignee | 1. Login to the System 2. Create a new task 3. Assign to a contractor. 4. Contractor will get a notification of a new task assigned to him and requires him/her to login to the system to process the task assigned. | Contractor's Email address | Every update or task assigned, the assignee/contractor will get a notifiation of a new task assigned to him/her through his/her registered email address in the system | No email received | Pass | mgr.ca.7523 | 5 -Task Management
TC-033 | Deployment to Test Server | Move the current server to our Testing Server | Test Server: 18.237.119.148 | All must be done in our Test server: 18.237.119.148 | The current test server is in HerukoApp | Pass | mgr.ca.7523 | 1 - User Role Tables Including Permissions and Login
TC-034 | Generate Error Report committed by the processing Contractors A & B after the QAing process | 1. QA will log the error committed either by processing contractor A & B 2. A system generated report will be available for the managers to see the accuracy of the output of the contractors | Submitted spreadsheet from Contractor A and B | A report will be available for the Manager's access to view the accuracy and compare the number of errors committed by the assigned contractors | n/a | Fail | mgr.ca.7523 | 7 -Report management | MGR 7523> Mon, Sep 13, 21 14:55> This is not generating reports, it's not showing the number of error rate collected from the QA. The interface is the same as shown in the List of Tasks | report management is working oct 4 > Done
TC-035 | Updating the existings user's details | View Users > Edit Users Update the data to be changed | Existing user data | First Name Last Name Username Email Address User Role Password all the above mentioned fields has to be updated or can be changed by the admin role | Not able to modify username and email address fields the Email address character is limited | Pass | mgr.ca.7523 | 1 - User Role Tables Including Permissions and Login |  | solved
TC-036 | Database |  | http://68.183.224.179/ | MariaDB or MySQL | SQL lite, no username and password | Pass | mgr.ca.7523 | change the main database to MySQL
T_ID 001 | Access the website | Enter the URL and try to laccess the website | Enter the valid URL Login the user | User should successfully land to Dashboard of system | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 002 | Login Screen with incorrent email | Enter the URL and try to login with invalid credentials by entering incorrect email and correct password | Enter the valid URL Login the user | System should generate an error of incorrect Email | It's showing Invalid Credentails | Pass | Tester | It's showing Invalid Credentails |  | done
T_ID 003 | Login Screen with incorrent Password | Enter the URL and try to login with invalid credentials by entering correct email and incorrect password | Enter the valid URL Login the user | System should generate an error of incorrect Email | It's showing Invalid Credentails | Pass | Tester | It's showing Invalid Credentails |  | done
T_ID 004 | Login Screen with incorrent Password & Email | Enter the URL and try to login with invalid credentials by entering incorrect email and password | Enter the valid URL Login the user | System should generate an error of incorrect Email | It's showing Invalid Credentails | Pass | Tester | It's showing Invalid Credentails |  | done
T_ID 005 | Login screen (Empty password field) | Enter only email in login screen and click the login and see the system behaviour | Enter the valid URL Login the user | As Password field is empty,system should a hint type message that pasword field is empty | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 006 | Login screen (Empty Email ID field) | Enter only password in login screen and click the login and see the system behaviour | Enter the valid URL Login the user | As Email ID field is empty,system should a hint type message thatEmail ID field is empty | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 007 | Login Screen (Empty email & password) | Login screen should handle the exceptions like clicking login without entering data | Enter the valid URL Login the user | As both fields are empty,system should a hint type message that Email ID and password field is empty | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 008 | Login Screen (Forgot Password) | Go to login screen and click forgot password to reset the password | Enter the valid URL Login the user | System should send the reset password link to user email | There is no option | Not started | Tester | There is no option available like "reset Password" | MGR 7523> Mon, Sep 13, 21 15:03> We will not add a Forgot password option. We will update passwords from Admin end. | In SOW,nothing mentioned about Forget PAssword
T_ID 009 | Login with valid credentials | Go to login screen and enter valid credentials to login | Enter the valid URL Login the user | User should be logged in successfully | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 010 | Dashboard | Verify user land on Dashboad | Enter the valid URL Login the user | User should land on Dashboard after login | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 011 | Dashboard | Verify there should be icon of home on Dashboard | Enter the valid URL Login the user | There should be home icon | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 012 | Dashboard | Click on Home icon | Enter the valid URL Login the user | Screen should get refresh | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 013 | Dashboard | There should be block of processes | Enter the valid URL Login the user | There should be block pf Process | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 014 | Dashboard | Verify tiles of All Process, Active, Complete, Pending | Enter the valid URL Login the user | Tiles related to process should be listed. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 015 | Dashboard | Click on tiles to open | Enter the valid URL Login the user | Screen of the process state should open | No screen is opened after clicking on the process tile | Fail | Tester | No screen is opened after clicking on the process tile | MGR 7523> Mon, Sep 13, 21 15:03> This was mentioned during our first meetings when you offered this dashboard design wherein I discussed this with you that the images should be clickable and linked to each respective pages. These are obvious features that are and supposed to be inclued in our current SoW, not with an excuse that it's not part of the SoW. | thats not mentioned in SOW,and its part of modification not error oct 1 >Done
T_ID 016 | Account Button | Verify account button at top right | Enter the valid URL Login the user | There should be button of account | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 017 | Account Button | Click on Account | Enter the valid URL Login the user | List of account related menu should populate | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 018 | Account Button | Verify menu of profile | Enter the valid URL Login the user | There should be option of profile | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 019 | Account Button | Verify Change Password option | Enter the valid URL Login the user | There should be option of Change Password | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 020 | Account Button | Verify Logout option | Enter the valid URL Login the user | There should be option of Logout | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 021 | Dashboard | Verify left window mwnu on screen | Enter the valid URL Login the user | There should be Window on left side of screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 022 | Dashboard | Verify menu of Dashbaord on left window | Enter the valid URL Login the user | There should be menu of Dashboard | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 023 | Dashboard | Click on Dashboard | Enter the valid URL Login the user Click on Dashboard | User should land on Dashboard screen. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 024 | Dashboard | Verify Home button on Dashboard screen | Enter the valid URL Login the user Click on Dashboard | There should be button of Home | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 025 | Dashboard | Click Home Button | Enter the valid URL Login the user Click on Dashboard Click on Home Button | User should land on home screen i-e Dashboard | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 026 | Templates | Verify Template menu in left window | Enter the valid URL Login the user | There should be menu of template | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 027 | Templates | Click Template menu | Enter the valid URL Login the user Click Templates | Drop down menu should get populate | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 028 | Templates | Verify Templates sub menu | Enter the valid URL Login the user Click Templates | There should be sub menu of template | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 029 | Templates | Click Template option under Template | Enter the valid URL Login the user Click Templates Click Sub menu templates | User should navigates to templates screen. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 030 | Templates | Verify list of templates | Enter the valid URL Login the user Click Templates Click Sub menu templates | There should be list of templates | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 031 | Templates | Verify Add New button on screen | Enter the valid URL Login the user Click Templates Click Sub menu templates | There should be button of Add New | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 032 | Templates | Click on Add New button | Enter the valid URL Login the user Click Templates Click Sub menu templates Click On Add New Button | User should navigate to Add New Form screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 033 | Templates | Submit Form detail with empty required fields | Enter the valid URL Login the user Click Templates Click Sub menu templates Click On Add New Button Enter all fields except required fields | System should generate error message | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 034 | Templates | Select Spreadsheet and upload word file | Enter the valid URL Login the user Click Templates Click Sub menu templates Enter all fields Select Spreadsheet and upload word file | Syastem should generate error message | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 035 | Templates | Select Workbook and upload excel file. | Enter the valid URL Login the user Click Templates Click Sub menu templates Click On Add New Button Enter all fields Select Workbook and upload excel file | System should generate error message | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 036 | Templates | Verify that columns of spreadsheet should be listed | Enter the valid URL Login the user Click Templates Click Sub menu templates Click On Add New Button Enter all fields Select Spreadsheet and upload excel file | Columns of spreadsheet should be listed. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 037 | Templates | Add Template | Enter the valid URL Login the user Click Templates Click Sub menu templates Click On Add New Button Enter all fields Click Submit | Template should get added. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 038 | Templates | Upload file without selecting file type and Submit | Enter the valid URL Login the user Click Templates Click Sub menu templates Click On Add New Button Upload File Donot select file type Click Submit | System should generate error message to select file type | Error screen appear with code. | Pass | Tester | It takes to a new page with some coded error message | file is not submitting without selecting the File | This will be Done
T_ID 039 | Templates | Verify sterik * sign with required fields | Enter the valid URL Login the user Click Templates Click Sub menu templates Click On Add New Button | There should be * sign with required fields | No * sign with required fields | Pass | Tester | There is No * sign | This is modification work ,no any error and not mentioned in SOW | done
T_ID 040 | Templates | Verify that added template listed in list of templates | Enter the valid URL Login the user Click Templates Click Sub menu templates Click On Add New Button Enter all fields Click Submit Go to Templates screen | Template should be listed on the screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 041 | Templates | Verify View button against tempalte | Enter the valid URL Login the user Click Templates Click Sub menu templates | There should be view button against template | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 042 | Templates | Click View Button | Enter the valid URL Login the user Click Templates Click Sub menu templates Click View Button | User should navigate to view template screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 043 | Templates | Verify user edit in view screen | Enter the valid URL Login the user Click Templates Click Sub menu templates Click View Button Edit fields | User should not be able to edit in view screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 044 | Templates | Verify Download File button on view screen | Enter the valid URL Login the user Click Templates Click Sub menu templates Click View Button | There should be button of Download on screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 045 | Templates | Click Download File Button | Enter the valid URL Login the user Click Templates Click Sub menu templates Click View Button Click Download File Button | File should get downloaded | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 046 | Templates | Verify Edit button against Template | Enter the valid URL Login the user Click Templates Click Sub menu templates | There should be button against each template | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 047 | Templates | Click Edit Button | Enter the valid URL Login the user Click Templates Click Sub menu templates Click on Edit Button | User should navigate to edit template screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 048 | Templates | Make Changes in Template | Enter the valid URL Login the user Click Templates Click Sub menu templates Click on Edit Button Make changes and Submit | Changes should be made successfully | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 049 | Templates | Change the name of template and Update | Enter the valid URL Login the user Click Templates Click Sub menu templates Click on Edit Button Change Name of Template and Submit | Name of template should get changed | Name of template remains same | Pass | Tester | not able to change the name | This is modification not any error | name is changing
T_ID 050 | Templates | Verify changes made in template | Enter the valid URL Login the user Click Templates Click Sub menu templates Click on Edit Button Make changes and Submit | Changes made in column should be reflecting | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 051 | Templates | Verify DELETE button against template. | Enter the valid URL Login the user Click Templates Click Sub menu templates | There should be delete button against template | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 052 | Templates | Delete template | Enter the valid URL Login the user Click Templates Click Sub menu templates Click Delete button | Template should get deleted | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 053 | Templates | Verify deleted template from list | Enter the valid URL Login the user Click Templates Click Sub menu templates Click Delete button | Deleted template should not be in the list | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 054 | Templates | Verify export button on the template screen. | Enter the valid URL Login the user Click Templates Click Sub menu templates | There should be button of export | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 055 | Templates | Click Export button | Enter the valid URL Login the user Click Templates Click Sub menu templates Click Export button | file should get downloaded | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 056 | Templates | Verify data in exported file | Enter the valid URL Login the user Click Templates Click Sub menu templates Click Export button Open exported files | Data should be same as of list | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 057 | Templates | Verify search fields on screen | Enter the valid URL Login the user Click Templates Click Sub menu templates | There should be field of search | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 058 | Templates | Make a valid search of template | Enter the valid URL Login the user Click Templates Click Sub menu templates Search Template | Template should get searched | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 059 | Templates | Make a invalid search of template | Enter the valid URL Login the user Click Templates Click Sub menu templates Make invalid Search Template | No template or record should found | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 060 | Templates | Verify sorting working fine on each column | Enter the valid URL Login the user Click Templates Click Sub menu templates Click Sorting arrows on column | list should get sort on basis of that column | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 061 | Templates | Verify pagination working fine1 | Enter the valid URL Login the user Click Templates Click Sub menu templates | Pagination should be working fine | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 062 | Templates | VerifyAdd Template sub-menu in left window under templates menu | Enter the valid URL Login the user Click Templates | There should be sub-menu of Add Template | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 063 | Templates | Click on Add Template | Enter the valid URL Login the user Click Templates Click Sub menu templates | User should navigate to Add Template screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 064 | Accounts | Verify Account Menu in left window | Enter the valid URL Login the user | There should be menu of Accounts | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 065 | Accounts | Click on Accounts | Enter the valid URL Login the user Click on Accounts | Dropdow menu should get populated | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 066 | Profile | Verify Profile sub-menu | Enter the valid URL Login the user Click on Accounts | There should be sub-menu Profile | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 067 | Profile | Click on Profile | Enter the valid URL Login the user Click on Accounts Click on Sub-menu Profile | User should navigate to Profile screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 068 | Profile | Verify details of Profile of user | Enter the valid URL Login the user Click on Accounts Click on Sub-menu Profile | Details of profile of user should be listed on it. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 069 | Profile | Make changes in profile and submit | Enter the valid URL Login the user Click on Accounts Click on Sub-menu Profile Make changes and Submit | Changes should be made successfully | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 070 | Profile | Verify changes made in Profile | Enter the valid URL Login the user Click on Accounts Click on Sub-menu Profile Make changes and Submit | Changes made should be reflecting | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 071 | Profile | Edit Username and User Role | Enter the valid URL Login the user Click on Accounts Click on Sub-menu Profile Change Username or User role and Submit | Username and User role should not get editted. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 072 | Change Password | Verify Change password option | Enter the valid URL Login the user Click on Accounts | There should be option of Change Password | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 073 | Change Password | Click Change password | Enter the valid URL Login the user Click on Accounts Click on Sub-menu Change Password | User should navigate to Change Password screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 074 | Change Password | Change password with invalid Current password | Enter the valid URL Login the user Click on Accounts Click on Sub-menu Change Password Enter invalid current password | System should generate error message | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 075 | Change Password | Change password with different New and Confirm Password | Enter the valid URL Login the user Click on Accounts Click on Sub-menu Change Password Enter different New and Confirm Passwrd Click Submit | System should generate error message | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 076 | Change Password | Change password with empty fields | Enter the valid URL Login the user Click on Accounts Click on Sub-menu Change Password Keep any field empty | System should generate error message | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 077 | Change Password | Change passwrd | Enter the valid URL Login the user Click on Accounts Click on Sub-menu Change Password Enter all fields Click Submit | Password should get changed | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 078 | Change Password | Login with old password | Enter the valid URL Login the user Click on Accounts Click on Sub-menu Change Password Enter all fields Click Submit Login with old password | User should not be logged in with old password | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 079 | Change Password | Login with new password | Enter the valid URL Login the user Click on Accounts Click on Sub-menu Change Password Enter all fields Click Submit Login with new password | User should get logged in with new password | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 080 | Logout | Verify Logout menu in the accounts menu | Enter the valid URL Login the user Click on Accounts | There should be option of Logout | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 081 | Logout | ClickLogout | Enter the valid URL Login the user Click on Accounts Click on Sub-menu Logout | User should get logout | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 082 | Users | Verify Users menu on left window | Enter the valid URL Login the user | There should be Menu of Users | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 083 | Users | Click Users | Enter the valid URL Login the user Click on Users | List of Sub-menus should get populated | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 084 | Users | Verify View users submenu | Enter the valid URL Login the user Click on Users | There should be view user sub menu in list | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 085 | View Users | Click View Users | Enter the valid URL Login the user Click on Users Click View User Sub-menu | User should navigate to Users screen. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 086 | View Users | Verify list of users on screen | Enter the valid URL Login the user Click on Users Click View User Sub-menu | List of Users should be visible | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 087 | View Users | Verify Add Users button on screen | Enter the valid URL Login the user Click on Users Click View User Sub-menu | There should be Add user button on screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 088 | View Users | Click on Add User button | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click Add User button | User should navigate to Add user form screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 089 | View Users | Add User with empty field | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click Add User button Enter all fields except required field Click Submit | System should generate error message | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 090 | View Users | Add user with invalid email | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click Add User button Enter all fields Enter invalid email Click Submit | System should generate error message | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 091 | View Users | Add user with different new and confirm apssword | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click Add User button Enter all fields Enter different password for new and confirm field Click Submit | System should generate error message | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 092 | View Users | Add User | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click Add User button Enter all fields Click Submit | User should get added succesfully | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 093 | View Users | Verify required fields with * sign | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click Add User button | There should be sign of * with required fields | There is no * sign | Pass | Tester | There is no * sign |  | added
T_ID 094 | View Users | Verify added user in list | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click Add User button Enter all fields Click Submit | User should be listed in list of user | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 095 | View Users | Verify View button against the user | Enter the valid URL Login the user Click on Users Click View User Sub-menu | There should be button of view user | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 096 | View Users | Click Users | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click View | user should get navigated to view screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 097 | View Users | Verify editing user in view mode | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click View Edit user | User should not be allowed to edit user in view mode | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 098 | View Users | Verify Edit button against user | Enter the valid URL Login the user Click on Users Click View User Sub-menu | There should be button of Edit user | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 099 | View Users | Click Edit Button | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click on Edit button | User should navigate to edit screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 100 | View Users | Edit user and submit | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click on Edit button Make changes and save | Changes should be made successfully | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 101 | View Users | Verify changes made | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click on Edit button Make changes and save | Changes should be reflected in user | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 102 | View Users | Verify to change username and email | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click on Edit button Make changes username and email Save | User should not be able to change username and email | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 103 | View Users | Verify Changes made in profile from Account should be reflected in view user details | Enter the valid URL Login the user Change profile from Accounts Click View user details | Changes made in profile should be reflected. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 104 | View Users | Verify to click Users menu from Manager account | Enter the valid URL Login the user from Manager account Click on User Click on Any user menus | Manager should be able to view users, add users, enable users, disable users | When manager click on these menu user get logout. | Pass | Tester |  | This will be solved | solved
T_ID 105 | View Users | Verify diable button against enable user | Enter the valid URL Login the user Click on Users Click View User Sub-menu | There should be button of disable | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 106 | View Users | Diable the enable user. | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click Disable button Click confirm | User get disable | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 107 | View Users | Verify user get disable | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click Disable button Click confirm | User should be disabled and enable button should be populating | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 108 | View Users | Verify enable button against diable user | Enter the valid URL Login the user Click on Users Click View User Sub-menu | There should be button of enable for disable user | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 109 | View Users | Enable the disable user | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click enable button Click Confirm | User should get enabled | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 110 | View Users | Verify user get enabled | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click enable button Click Confirm | User should get enabled and disable button should be populating | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 111 | View Users | Verify export button on the screen | Enter the valid URL Login the user Click on Users Click View User Sub-menu | There should be button of export | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 112 | View Users | Click export button | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click Export Button | file should get downloaded | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 113 | View Users | Open the file downloaded | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click Export Button | Downloaded file should get nopened | Error occurs while opening the file | Pass | Tester | Error occurs while opening the file | Data is modifying on server Dynamically and nothing can be done in this case as server is responsible for this | done
T_ID 114 | View Users | Verify sorting working on screen | Enter the valid URL Login the user Click on Users Click View User Sub-menu Click Sorting arrows | Columns should get sorted | Same as expected | Pass | Tester | Passed from PRJ 0722 | or once you purchase the domain and add ssl this problem might be solved
T_ID 115 | View Users | Verify pagination working fine | Enter the valid URL Login the user Click on Users Click View User Sub-menu | Pagination should be working fine | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 116 | View Users | Verify search field on the screen | Enter the valid URL Login the user Click on Users Click View User Sub-menu | There should be search field | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 117 | View Users | Search the valid user | Enter the valid URL Login the user Click on Users Click View User Sub-menu Search valid user | User should get searched | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 118 | View Users | Search invalid user | Enter the valid URL Login the user Click on Users Click View User Sub-menu Search invalid user | Research should show no result. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 119 | Add User | Verify Add user on left window pan | Enter the valid URL Login the user Click on Users | There should be menu of Add user | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 120 | Add User | Click on Add User sub-menu under Users | Enter the valid URL Login the user Click on Users Click Add User Sub-menu | User should navigate to Add user screen. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 121 | Enabled Users | Verify Enable user on left window pan | Enter the valid URL Login the user Click on Users | There should be sub-menu of Enable user | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 122 | Enabled Users | Click on Enable User sub-menu under Users | Enter the valid URL Login the user Click on Users Click Enable User Sub-menu | User should navigate to enable user screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 123 | Enabled Users | Enable single user | Enter the valid URL Login the user Click on Users Click Enable User Sub-menu Select single user Click Enable button | User should get enabled | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 124 | Enabled Users | Enable multiple users | Enter the valid URL Login the user Click on Users Click Enable User Sub-menu Select multiple users Click Enable button | Users should get enabled. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 125 | Enabled Users | Verify enabled users | Enter the valid URL Login the user Click on Users Click Enable User Sub-menu Select multiple users Click Enable button Go to View users | Status of user should be enabled | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 126 | Enabled Users | Verify already enabled users should not get added in field | Enter the valid URL Login the user Click on Users Click Enable User Sub-menu Select already enabled user Click Enable button | Already enabled user should not be listed. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 127 | Disabled Users | Verify Disable user on left window pan | Enter the valid URL Login the user Click on Users | There should be sub-menu of Disable user | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 128 | Disabled Users | Click on disable User sub-menu under Users | Enter the valid URL Login the user Click on Users Click disable User Sub-menu | User should navigate to disable user screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 129 | Disabled Users | Disable single user | Enter the valid URL Login the user Click on Users Click Enable User Sub-menu Select single user Click disable button | User should get disabled | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 130 | Disabled Users | Disable multiple users | Enter the valid URL Login the user Click on Users Click Enable User Sub-menu Select multiple users Click Disable button | Users should get disabled. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 131 | Disabled Users | Verify disabled users | Enter the valid URL Login the user Click on Users Click Enable User Sub-menu Select multiple users Click Disable button Go to View users | Status of user should be enabled | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 132 | Disabled Users | Verify already disabled users should not get added in field | Enter the valid URL Login the user Click on Users Click Disable User Sub-menu Select already enabled user Click Enable button | Already disabled user should not be listed. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 133 | Change User Password | Verify Change user password sub-menu in left window | Enter the valid URL Login the user Click on Users | There should be sub-menu of Change User password | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 134 | Change User Password | Click Change userpassword | Enter the valid URL Login the user Click on Users Click Change User Password Sub-menu | User should navigate to change user password screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 135 | Change User Password | Enter password to set for user | Enter the valid URL Login the user Click on Users Click Change User Password Sub-menu Enter new and confirm password | Password of user should get changed | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 136 | Business Processes | Verify Business Processes in left window menu | Enter the valid URL Login the user | there should be menu in left window pan | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 137 | Business Processes | Click on Business Processes | Enter the valid URL Login the user Click on Business Process | Sub-menus of Business processes should get populated | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 138 | All Processes | Verify All Processes sub-menu under Business Process menu | Enter the valid URL Login the user Click on Business Process | There should be sub-menu All Processes | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 139 | All Processes | Click All Processes | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu | User should navigate to All Processes screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 140 | All Processes | Verify Add New Button on screen | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu | There should be button of Add New | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 141 | All Processes | Click Add New Button | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Add New Button | User should navigate to Add Business Process screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 142 | All Processes | Add Process with empty required fields | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Add New Button Enter all fields except required | System should show error message | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 143 | All Processes | Add Process with Contractor A and Contrator B same | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Add New Button Enter all fields Keep Contrator A and B same | System should show error message | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 144 | All Processes | Add Process with empty contrator and QA fields | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Add New Button Enter all fields Keep Contrator A and B and QA Contractor empty. | System should show error message (to fill this field | It shows Contractor A and B can't be same even they are not selected | Pass | Tester | It shows Contractor A and B can't be same even they are not selected | When you keep both users empty | done
T_ID 145 | All Processes | Add Process with different file upload and seleted file type | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Add New Button Enter all fields Select file type different and upload different type | System should generate error message | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 146 | All Processes | Add Process with past date | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Add New Button Enter all fields Enter past date Click Submit | System should not allow to enter past date | Same as expected | Pass | Tester | Passed from PRJ 0722 | UserA = empty
T_ID 147 | All Processes | Add Process | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Add New Button Enter all fields Click Submit | Process should get added | It's showing error in creating new process | Pass | Tester | It's showing error in creating new process | UserB = Empty | check the error code
T_ID 148 | All Processes | Verify the status of newly created process | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Add New Button Enter all fields Click Submit | Status of newly started process should be Pending | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 149 | All Processes | Verify added process in the list | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Add New Button Enter all fields Click Submit | Process should be listed | Same as expected | Pass | Tester | Passed from PRJ 0722 | empty=empty
T_ID 150 | All Processes | Verify View button against the process | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu | There should be view button against template | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 151 | All Processes | Click View Button | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click View button | User should navigate to View screen | Same as expected | Pass | Tester | Passed from PRJ 0722 | thats why its displaying this error
T_ID 152 | All Processes | Verify user add in edit mode | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click View button | User should not allowed to edit the process | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 153 | All Processes | Verify details in View screen | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click View button | Details of contractors should be listed as filled | Same as expected | Pass | Tester | Passed from PRJ 0722 | and the thing you are saying is modification not error
T_ID 154 | All Processes | Verify Delete button against the process | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu | There should be delete button against process | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 155 | All Processes | Click Delete button | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Delete Button | Process should get deleted | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 156 | All Processes | Verify deleted process from the list | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Delete Button | Process should not remain in the list | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 157 | All Processes | Vedrify search field on screen | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu | There should be field of search | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 158 | All Processes | Make a valid search of process | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Make a search | Process should get searched and appear in list | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 159 | All Processes | Make a invalid search of process | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Make a invalid search | No match should found of process | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 160 | All Processes | Verify export button on screen | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu | There should be export button on screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 161 | All Processes | Click Export button | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Export Button | File should get downloaded | Same as expected | Pass | Tester | Passed from PRJ 0722 | same as T_ID 113
T_ID 162 | All Processes | Open the downloaded file | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Export Button open downloaded file | File should open properly | Error occurred that file is unsafe | Pass | Tester | Error |  | Data is modifying on server Dynamically and nothing can be done in this case as server is responsible for this
T_ID 163 | All Processes | Verify sorting arrows on columns | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu | Sorting arrows should be on screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 164 | All Processes | Test the sorting functionality | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click sorting arrows | Sorting of columns should be working | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 165 | All Processes | Verify pagination working fine | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Test pagination | Pagination should be working fine | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 166 | Start New Process | Verify Start New Processes sub-menu under Business Processes | Enter the valid URL Login the user Click on Business Process | There should be sub-menu of Start new peocess | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 167 | Start New Process | Click Start New Processes | Enter the valid URL Login the user Click on Business Process Click on Start New Processes | User should navigate to Start New Proces screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 168 | Completed Processes | Verify Completed Processes sub-menu under Business Process | Enter the valid URL Login the user Click on Business Process | There should be sub-menu of Completed Processes | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 169 | Completed Processes | Click on Completed processes | Enter the valid URL Login the user Click on Business Process Click on Completed Processes | User should navigate to completed process | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 170 | Completed Processes | Verify list of Completed process on the screen. | Enter the valid URL Login the user Click on Business Process Click on Completed Processes | There should be list of completed processes | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 171 | Completed Processes | Vedrify search field on screen | Enter the valid URL Login the user Click on Business Process Click on Completed Processes | There should be field of search | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 172 | Completed Processes | Make a valid search of process | Enter the valid URL Login the user Click on Business Process Click on Completed Processes Make a search | Process should get searched and appear in list | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 173 | Completed Processes | Make a invalid search of process | Enter the valid URL Login the user Click on Business Process Click on Completed Processes sub menu Make a invalid search | No match should found of process | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 174 | Completed Processes | Verify export button on screen | Enter the valid URL Login the user Click on Business Process Click on Completed Processes sub menu | There should be export button on screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 175 | Completed Processes | Click Export button | Enter the valid URL Login the user Click on Business Process Click on All Processes sub-menu Click Export Button | File should get downloaded | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 176 | Completed Processes | Open the downloaded file | Enter the valid URL Login the user Click on Business Process Click on Completed Processes sub menu Click Export Button open downloaded file | File should open properly | Error occurred that file is unsafe | Pass | Tester | Error | same as T_ID 113 | Data is modifying on server Dynamically and nothing can be done in this case as server is responsible for this
T_ID 177 | Completed Processes | Verify sorting arrows on columns | Enter the valid URL Login the user Click on Business Process Click on Completed Processes sub menu | Sorting arrows should be on screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 178 | Completed Processes | Test the sorting functionality | Enter the valid URL Login the user Click on Business Process Click on Completed Processes sub menu Click sorting arrows | Sorting of columns should be working | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 179 | Completed Processes | Verify pagination working fine | Enter the valid URL Login the user Click on Business Process Click on Completed Processes sub menu Test pagination | Pagination should be working fine | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 180 | Active Processes | Verify sub-menu of Active Processes under Business Processes | Enter the valid URL Login the user Click on Business Process | There should be sub-menu of active processes | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 181 | Active Processes | Click Active Processes | Enter the valid URL Login the user Click on Business Process Click on Active Processes sub menu | User should navigate to Active processes screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 182 | Pending Processes | Verify sub-menu of Pending Processes under Business Processes | Enter the valid URL Login the user Click on Business Process | There should be sub-menu of Pending processes | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 183 | Pending Processes | Click Pending processes | Enter the valid URL Login the user Click on Business Process Click on Pending Processes sub menu | User should navigate to Pending processes screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 184 | Pending Processes | Verify pending processes for each contractor A and B seperately | Enter the valid URL Login the user Click on Business Process Click on Pending Processes sub menu | Processes should be listed seperately for each contractor A and B | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 185 | Pending Processes | Verify process of contractor B should show detail of contractor B | Enter the valid URL Login the user Click on Business Process Click on Pending Processes sub menu Click View button of Contractor B | Details of Contractor B should be visible | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 186 | Report | Verify Report menu in left window pan | Enter the valid URL Login the user | There should be menu of Reprots | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 187 | Report | Click Reports | Enter the valid URL Login the user Click Reports | Sub-menu of report should get populated | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 188 | View Reports | Verify View Reports sub-menu | Enter the valid URL Login the user Click Reports | There should be sub-menu of View Report | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 189 | View Reports | Click View Reports | Enter the valid URL Login the user Click Reports Click View Reports | Usere should navigate to view reports screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 190 | View Reports | Verify list of reports | Enter the valid URL Login the user Click Reports Click View Reports | There should be list of reports | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 191 | View Reports | Verify two reports of one process containing two contractors A and B | Enter the valid URL Login the user Click Reports Click View Reports | There should be two reports of each process | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 192 | View Reports | Verify View button against process | Enter the valid URL Login the user Click Reports Click View Reports | There should be View button against process | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 193 | View Reports | Click View Button | Enter the valid URL Login the user Click Reports Click View Reports Click View button | User should navigate to View process screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 194 | View Reports | Verify to edit the report | Enter the valid URL Login the user Click Reports Click View Reports Click View button make changes | User should not able to edit in vieew mode. | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 195 | View Reports | Vedrify search field on screen | Enter the valid URL Login the user Click Reports Click View Reports | There should be field of search | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 196 | View Reports | Make a valid search of process | Enter the valid URL Login the user Click Reports Click View Reports Make a search | Process should get searched and appear in list | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 197 | View Reports | Make a invalid search of process | Enter the valid URL Login the user Click Reports Click View Reports Make a invalid search | No match should found of process | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 198 | View Reports | Verify export button on screen | Enter the valid URL Login the user Click Reports Click View Reports | There should be export button on screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 199 | View Reports | Click Export button | Enter the valid URL Login the user Click Reports Click View Reports Click Export Button | File should get downloaded | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 200 | View Reports | Open the downloaded file | Enter the valid URL Login the user Click Reports Click View Reports Click Export Button open downloaded file | File should open properly | Error occurred that file is unsafe | Pass | Tester | Error | same as T_ID 113 MGR 7523> Fri, Aug 27, 21 15:12> The Error added by the QA is not reflecting in the Reports section, there's no counting. | Data is modifying on server Dynamically and nothing can be done in this case as server is responsible for this
T_ID 201 | View Reports | Verify sorting arrows on columns | Enter the valid URL Login the user Click Reports Click View Reports | Sorting arrows should be on screen | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 202 | View Reports | Test the sorting functionality | Enter the valid URL Login the user Click Reports Click View Reports Click sorting arrows | Sorting of columns should be working | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 203 | View Reports | Verify pagination working fine | Enter the valid URL Login the user Click Reports Click View Reports Test pagination | Pagination should be working fine | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 204 | Process Completion | vVerify at contract account pending process should be listed | Login to Contractor A account Go to task menu Click View task | There should be pending task listed | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 205 | Process Completion | Marked the task started | Login to Contractor A account Go to task menu Click View task Download the file of task | Process should get marked started | Same as expected | Pass | Tester
T_ID 206 | Process Completion | Mark for pending approval | Login to Contractor A account Go to task menu Click View task Submit the fiel making changes | Process should marked for approval | Same as expected | Pass | Tester
T_ID 207 | Process Completion | Verify at contractor B account pending process should be listed | Login to Contractor B account Go to task menu Click View task | There should be pending task listed | Same as expected | Pass | Tester
T_ID 208 | Process Completion | Marked the task started from Contractor B | Login to Contractor B account Go to task menu Click View task Download the file of task | Process should get marked started | Same as expected | Pass | Tester
T_ID 209 | Process Completion | Mark for pending approval from Contractor B | Login to Contractor B account Go to task menu Click View task Submit the fiel making changes | Process should marked for approval | Same as expected | Pass | Tester
T_ID 210 | Process Completion | Verify Pending Approval tasks from QA Contractor account | Login Qa Contractor Go to Pending Approval menu | There should be process listed | Same as expected | Pass | Tester
T_ID 211 | Process Completion | Add Feedback for the Process | Login Qa Contractor Go to Pending Approval menu Click On View the proess Add Feedback | Fedback should get added | Same as expected | Pass | Tester
T_ID 212 | Process Completion | Marked the process as approved | Login Qa Contractor Go to Pending Approval menu Click On View the proess Add Feedback Click Submit as Approved Process | Process get approved | Same as expected | Pass | Tester
T_ID 213 | Process Completion | Verify from the admin account process should get added in Completed process menu | Login to Admin account GO to Completed Processes | Process completed should get start appearing in the list | Same as expected | Pass | Tester | Passed from PRJ 0722
T_ID 214 | Specifications | Upload the excel file with mulitole sheets | Login the user Go to business process Upload the the excel with mulitple sheets | It shoud get uploaded | Same as expected | Pass | Tester
T_ID 215 | Specifications (Data obfuscation) | Verify that columns of other sheet should get included | Login the user Go to business process Upload the the excel with mulitple sheets Include the columns | Cloumns of other should alos get included. | Same as expected | Pass | Tester
T_ID 216 | Specifications (Data obfuscation) | Verify after perocessing file include only selected included columns | Login the user Go to business process Upload the the excel Include the columns | After processing file should have only included columns | Same as expected | Pass | Tester
T_ID 217 | Specifications (Data obfuscation) | Verify that masking has been done | Login the user Go to business process Upload the the excel Include the columns | Masking should be done and replace with dummy names | Same as expected | Pass | Tester
T_ID 218 | Specifications (Name conventions) | Verify that name of file downloaded by Contractor A | Login the user Go to business process Upload the the excel Login with contractor A Go to Pending Task Click view button Click Download file | Name of file should include name of contractor | Same as expected | Pass | Tester
T_ID 219 | Specifications (Data obfuscation) | Verify that changes made upload the other file for contractor A | Login the user Go to business process Upload the the excel Login with contractor A Go to Pending Task Click view button Click Download file Make changes Upload different file and submit | system should generate message to upload downloaded file | Same as expected | Pass | Tester
T_ID 220 | Specifications (Data obfuscation) | Verify that changes made upload the downloaded file For contractor A | Login the user Go to business process Upload the the excel Login with contractor A Go to Pending Task Click view button Click Download file Make changes Upload downloaded file and submit | file should get uploaded | Same as expected | Pass | Tester
T_ID 221 | Specifications (Data obfuscation) | Verify field get masked in downloaded file of contractor A | Login the user Go to business process Upload the the excel Login with contractor A Go to Pending Task Click view button Click Download file | Data should be obfuscated | Same as expected | Pass | Tester
T_ID 222 | Specifications (Naming conventions) | Verify that name of file downloaded by Contractor B | Login the user Go to business process Upload the the excel Login with contractor B Go to Pending Task Click view button Click Download file | Name of file should include name of contractor | Same as expected | Pass | Tester | MGR 7523> Thu, Jul 15, 21 07:11> It's not the name of the contractor to be included in the filename it's only A or B. The file naming convention didn't follow the correct format.
T_ID 223 | Specifications (Data obfuscation) | Verify that changes made upload the other file for contractor B | Login the user Go to business process Upload the the excel Login with contractor B Go to Pending Task Click view button Click Download file Make changes Upload different file and submit | system should generate message to upload downloaded file | Same as expected | Pass | Tester
T_ID 224 | Specifications (Data obfuscation) | Verify that changes made upload the downloaded file For contractor B | Login the user Go to business process Upload the the excel Login with contractor B Go to Pending Task Click view button Click Download file Make changes Upload downloaded file and submit | file should get uploaded | Same as expected | Pass | Tester
T_ID 225 | Specifications (Data obfuscation) | Verify field get masked in downloaded file of contractor B | Login the user Go to business process Upload the the excel Login with contractor B Go to Pending Task Click view button Click Download file | Data should be obfuscated | Same as expected | Pass | Tester
T_ID 226 | Specifications (Data obfuscation) | Verify that after approval submission from Contractors..Process goes to QA contractor | Login the user Go to business process Upload the the excel Login with contractor B Go to Pending Task Click view button Click Download file Make changes Upload downloaded file and submit Login to QA Contractor Go to to Pending Process | Process should be listed in that list | Same as expected | Pass | Tester
T_ID 227 | Specifications (Data obfuscation) | Download the file and verify mask data from QA account | Login the user Go to business process Upload the the excel Login with contractor B Go to Pending Task Click view button Click Download file Make changes Upload downloaded file and submit Login to QA Contractor Go to to Pending Process Click View and download the files | files should have data masked | Same as expected | Pass | Tester
T_ID 228 | Specifications (Data obfuscation) | Verify Changes made by contractors A and B should be visible in QA Downloaded files | Login the user Go to business process Upload the the excel Login with contractor B Go to Pending Task Click view button Click Download file Make changes Upload downloaded file and submit Login to QA Contractor Go to to Pending Process Click View and download the files | Changes made by co ntractor should be listed in downloaded file | Same as expected | Pass | Tester
T_ID 229 | Specifications (Data obfuscation) | Mark the file as approved with feedback | Login the user Go to business process Upload the the excel Login with contractor B Go to Pending Task Click view button Click Download file Make changes Upload downloaded file and submit Login to QA Contractor Go to to Pending Process Click View and download the files Click Mark aas approved and feedback | Process get approved and feedback added. | Same as expected | Pass | Tester
T_ID 230 | Specifications (Data obfuscation) | Verify the completed process | Login the user Go to business process Upload the the excel Login with contractor B Go to Pending Task Click view button Click Download file Make changes Upload downloaded file and submit Login to QA Contractor Go to to Pending Process Click View and download the files Click Mark aas approved and feedback Login the user who created process Go to completed process | Process should be listed in completed | Same as expected | Pass | Tester
T_ID 231 | Specifications (Data obfuscation) | Verify the data obfuscated unmasked in completed downloaded file | Login the user Go to business process Upload the the excel Login with contractor B Go to Pending Task Click view button Click Download file Make changes Upload downloaded file and submit Login to QA Contractor Go to to Pending Process Click View and download the files Click Mark aas approved and feedback Login the user who created process Go to completed process Download the file | Data masked will be back to unmasked and orinal data will be listed. | Same as expected | Pass | Tester
T_ID 232 | Specifications | Verify columns deleted as not included | Login the user Go to business process Upload the the excel with mulitple sheets Select included column | Columns should get deleted which are not included. | Same as expected | Pass | Tester
T_ID 233 | Specifications | Try to edit files in the app | Login the user Open the file or edit in application | User cannot edit the file in application. It should be edited in excel or other external file. | Same as expected | Pass | Tester
T_ID 234 | Specifications | Edit the file externally | Login the user Open the file or edit in Excel outside of application | File should get editted | Same as expected | Pass | Tester
T_ID 235 | Specifications (Reports) | Verify Reports count | Login the user Go to view reports | There should be entry of each process started | Same as expected | Pass | Tester
T_ID 236 | Specifications (Reports) | Verify time of each action performed against the process by contractors | Login the user Go to view reports | Time and date should be accurate. | Same as expected | Pass | Tester
T_ID 237 | Specifications (Reports) | Verify status of process of each report | Login the user Go to view reports | Status of process should be listed against each process. | Same as expected | Pass | Tester
T_ID 238 | Add User | Check the max characters to be indicated in each text box | Login to user Users > Add User Enter all the fields value Click submit | View the list in the Users tab All data are correct and intact | The email textbox somehow has limited length of character. The email address added in the user eg., dylanmartinez701@protonmail.com didn't record the complete email, hence makng the email address incorrect | Pass | mgr.ca.7523 |  |  | solved
T_ID 239 | Task | Assigned contractor received an email to his/her registered email address of the assigned task. |  |  | No email notifcation received from the app to the contractor's registered email address | Pass | mgr.ca.7523 |  |  | email is sending
| Business Processes | Templates > Add New Template | Add New Business Process Template | Employee or Manager or Team Leader Role is able to add links to the procedures for contractor and employee | No textboxes to add the link to the procedure for Employee and for Contractor | Fail | mgr.ca.7523 |  |  | links are automatically generated ( task links also sent in email automatically)
| Date and Time Format | All menus and lists | All list | Date and time must be in a format of DD MM YYYY hh:mm:ss (eg., 25 August 2021 13:01:51) | MM DD YYYY hh:mm am/pm eg., Aug. 18 2021 4:46 am or Aug. 26, 2021, midnight | Fail | mgr.ca.7523 |  |  | done
| Update Template Fields | Add new Templates Update Template fields | Business Process Template | The template columns/fileds should be set on default as Not Included, that is the checkbox of Include should be checked. | MGR 7523> Mon, Sep 13, 21 15:21> Default value is selected even if the checkbox is not enabled. | Fail | mgr.ca.7523 |  |  | default checkbox value is updated and its included
| Email Notification sent to A & B Contractors | 1. Create a new Business Process (Task) 2. Assign to A, B and QA Contractors 3. All assignees received email notifications of the assigned tasks | Business Process | They should receive this kind of email format: Subject: You've been assigned a new task <name of the task> Dear Processing Contractor <First Name>, Please complete the following task according to your contract with us. Click this link to open the instructions for the task: <link> Click this link when you start the task: <link> Click this link when you have completed the task: <link>, then reply to this email, attaching the completed files you worked on. Thank you, <employee first name> | Sample of the actual email notfiication received: Subject: You've been assigned a new task Dear BDM Please complete the following task according to your contract with us. Thank you Admin Click this link to open the Task http://68.183.224.179/process/pc-task-detail/16 * There's no link for the procedure to follow. | Fail | mgr.ca.7523 |  | MGR 7523> Fri, Sep 10, 21 07:16> Please follow exactly the template subject and content. Also, please take note: Add two links in the body which, when clicked, alert the application to change the status of the assigned tasks in the database: Click this link to open the instructions for the task. Click this link when you start the task. Click this link when you have completed the task, then reply to this email, attaching the completed files you worked on. (when clicked, hit reply all and allow the Processing Contractor to manually attach the files and edit the email body. There is no link to log in to the app because we won’t be giving this to all Processing Contractors, however a login account will always be created, just not necessarily given to every Processing Contractor and QA Contractor. If it is given, it will be given manually. | checked the email link (Enter valid email to receive the valid link)
| Email Notification sent to QA Contractor | 1. A & B Contractors both submitted their assigned tasks 2. QA Contractor get notification | Business Process | The QA contractor should receive this email notification: Subject: You've been assigned a new QA task <name of the task> Dear QA Contractor <First Name>, Please complete the following task according to your contract with us. Click this link to open the instructions for the task: <link> Click this link when you start the task: <link> Click this link when you have completed the task: <link>, then reply to this email, attaching the completed files you worked on. Thank you, <employee first name> | none | Fail | mgr.ca.7523 |  | Q&A contractor is sent an email from the app, same method as for the Processing Contractors or logs in to the app via the GUI if access credentials have been given. If web interface, Q&A contractor downloads the A&B files and compares them using another application and identifies and corrects errors and indicates in the app or email reply how many errors were made by each of A and B. When done, Q&A contractor uploads or emails the files, same method as for Processing Contractors. The application renames the files according to the same naming convention but with Q on the end instead of A or B and the date and time are also updated for each file. Payroll Leave_Leave Credit Processing_Auckland Office_20210323_1418_Q After QA uploads the files the app will make a copy of each file, change the filename by replacing Q with C (for completed) then replace all the processing data wiand the real data again, replacing from the database the processing names and numbers with the real names. For deleted records, these are simply skipped. | if i add the notification link to the qa contractor as well it will change the whole procedure/logic as you mentioned that qa contractor will recive/see the task only when bith process contractor submit tasks . In email it will show when task is crated
| QA Dashboard is showing there's a new task assigned even if the assignees (A & B) didn't yet submit their tasks completed. | Login to QA Contractor account Dashboard | QA Contractor | If there's no A and B agents who submitted completed tasks, there's no available tasks to be shown in QA contractor's dashboard | There's an indication in the dashboard that there's a task, wherein the task can be viewed even the agents didn't submit or only 1 of them submit | Fail | mgr.ca.7523
| Filename of QA Contractor after downloading the submitted files | Login to QA Contractor account Tasks > To be Checked | QA Contractor Submitted A & B tasks | The downloaded files submitted by A & B contractors should follow the correct naming convention. The application renames the files according to the same naming convention but with Q on the end instead of A or B and the date and time are also updated for each file. Payroll Leave_Leave Credit Processing_Auckland Office_20210323_1418_Q | It didn't added a Q to the filename but a random filename like this: Task_Payroll_Sample_20210913_ad_3522_o8hY4mj Task_Payroll_Sample_20210913_ia_3301_UX7sQtD | Fail | mgr.ca.7523 |  |  | files naming conventions are done automatically .ie in one folder if there is a file abc.txt we cant add new file with same name ,new file will be added as abc1.txt or abc(copy).txt
Field Validations
Users | Add User | First name fields and Last name field should not allow to enter numbers.
| Enabled User | There should be limit of chracters entered into the field to search the user from dropdown User is able to enter long paragragh
| Disabled User | There should be limit of chracters entered into the field to search the user from dropdown User is able to enter long paragragh
Templates | Add Template | There should be limit of chracters on Process name field in Add Templates as it get lengthy in templates list.
Accounts | Profile | First name fields and Last name field should not allow to enter numbers.
First name fields and Last name field should have limit of chracters.
Website |  | Logo of the Website should be on the top
Note on A1: ID number of the Test Case
Note on B1: This should describe the functionality of a product or software application's feature to be tested
Note on C1: These are set of steps to be carried out in order to test the specified scenario which is the mentioned specific feature of an application or product.
Note on D1: These are the products or the application's data to be used in order to process the testing.
Note on E1: The result that the project is aiming to achieved.
Note on F1: This is the real result after doing the said testing. It can be opposite to the expected result or the test was able to prove and obtain the expected result
Note on G1: Status of the Result of the testing. It's a Pass status if it meets the expected result otherwise, fail if it didn't.
Note on H1: The assignee who did the testing

## Database Table
Table Name | Fields | Description | Type | Comments
Users | first_name | first name of the user | text(25)
| last_name | surname/family name of the user | text(25)
| job_title | position/role of the user | text(30)
| user_id | specific user id based on the naming convention | varchar(20)
| email_address | registered email address of the user | varchar(30)
| user_category | access level of the user (manager, Team Leader, contractor, employee etc.) | text(30)
| user_id | auto increment | int (auto increment)
| timezone | timezone where the user is currently located, e., option is +08 or -08 | varchar(3)
PersonProcessingNames | id | auto increment | int (auto increment) | https://www.verywellfamily.com/top-1000-baby-boy-names-2757618 https://www.verywellfamily.com/top-1000-baby-girl-names-2757832 http://www2.census.gov/topics/genealogy/2000surnames/Top1000.xls
| identifying_no | user input based on the naming convention format | varchar(20)
| gender | input as M or F | text(1)
| first_name | first name of the person | text(50)
| middle_name | middle name | text(50)
| middle_initial | initial of the middle name | text(1)
| last_name | surname/family name | text(50)
| nationality | foreign key from nationality table
BusinessProcessingNames | id | auto increment | int (auto increment)
| customer_no | user input based on the naming convention format | varchar(20)
| business_name | name of the business company | varchar(50)
| nationality | country where the head office is located
BusinessProcessTemplate | name | title of the business process | varchar(150)
| link_to_procedure | link url of the procedure which describes to the contractor how to do the task | longtext
| business_process_template_id | unique id of the business process template; user input based on naming convention | varchar(10)
| id | auto increment | int (auto increment)
BusinessProcessRun | business_process_template_id | foreign key; the business process id of the template used | varchar(10)
| business_process_id | unique id of the business process being triggered/run | varchar(10)
| user_id | foreign key, user id of the user that created the business process task. | varchar(10)
| created_at | date and time the task added | datetime
| assigned_dt_pc | date and time the task assigned to the contractor | datetime
| assigned_dt_qa | date and time the task assigned to the QA | datetime
| due_date | date the task is to be completed by the assignee | date
Files | file_id
| uploaded_by_user_category | Flag to indicate whether uploaded by user, Processing Contractor or QA Contractor | text(20)
| uploaded_by_user_id | user id of the user who uploaded the file | varchar(10)
| name_of_file | name of the uploaded file | varchar(50)
| name_of_sheet | name of each sheet tab if the file is spreadsheet and has multiple sheets to be uploaded one at a time. | varchar(20) | mgr.mr.0951> Fri, Apr 16, '21 10:46 AM> this design would only allow one sheet name. You need another table for sheet names. MGR 7523> Wed, Apr 21, 21 16:14> But this is per upload right? mgr.mr.0951> Thu, Apr 22, '21 11:04> a spreadsheet might have more than one sheet and each sheet is a separate spreadsheet as far as our app is concerned. So you need to upload the name of each sheet, not just the name of the file. MGR 7523> Thu, Apr 22, 21 14:07> noted. name_of_sheet column is included.
| file_format | format of the file (eg., xls, xlsx, csv) | varchar(10)
| date_time_uploaded | date and time the file was uploaded | datetime
| business_process_id | foreign key; id of the business process task | varchar(10)
| recurring_freq | if this is recurring or one time | varchar(15)
| date_time_assigned | the date and time the file has been assigned/given to the assignee | datetime
| status_id | foreign key; unique id of status table | varchar(10)
| file_blob | File blob or native file immutable copy of the encrypted file stored in the database for audit purposes: as originally uploaded by the employee 1. As uploaded by each of the two Processing Contractors 2. As uploaded by QA Contractor 3. As finally approved by the employee after further edits | blob
nationality | nationality_id | auto increment | int | https://pypi.org/project/country-list/
| country_of_residence | populate all the list of countries | text(30) | https://www.sitekickr.com/snippets/python/list-countries
| nationality | populate all the list of nationalities | text(30)
| language_id | foreign key of language table, being the most used national language of the nationality
| timezone | foreign key of timezone table
status | id | auto increment | int
| status_id | unique status id based on user input following a naming convention | varchar(10)
| status | name or title of the status Statuses such as: New Contractor Assigned QA Assigned Contractor Work Started QA Work Started Completed Cancelled | text(20)
| description | brief explanation of what the status means | text(100)
languages | language_id
| contractor_id |  |  | https://pypi.org/project/country-list/
| languages | list of human languages in which the contractor is either fluent or native for reading / writing.
ErrorCount | business_process_id | foreign key from BusinessProcessRun table. | int
| user_id | foreign key, the id of the contractor that is assigned to process the task | varchar(10)
| error_count | number of error the contractor committed on the assigned task | int
timezone | timezone_id
gmt_offset
nationality_id

## Data
Status | Rendered by
- | -
Not started | Tester
Pending | mgr.ca.7523
Pass
Fail
Note on B1: The assignee who did the testing